## Risks
LinkedHU_CENG - Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2022-04-29 | Team Member Has Left the Team | Some members of the team have left the group before the completion of the project. | P | 5 | 25% | 1.25 | Project Manager | Reorganize the responsibilities and the team to lessen the impact of the team member's absence. Inform the stakeholders about possible delays. Team members should motivate each other for a quick adaptation.
2 | 2022-03-18 | Team Member Not Available Due to Health Reasons | Some members of the team are ill and not available. | P | 2 | 50% | 1 | Project Manager | Rearrange the tasks and team to minimize the impact of the absence of the team member.
3 | 2022-05-05 | Time Required for Completion of The Development Is Underestimated | The time needed to complete the software is underestimated. | E | 4 | 50% | 2 | Project Manager | Investigate buying-in components; investigate use of a program generator.Inform the stakeholders about the situation, increase efforts to develop the project.Implement critical use cases, demand extensions to deadlines if necessary.
4 | 2022-04-06 | Framework Change | The underlying technology is replaced by another due to the chosen one's inability to match the project's needs or failure to implement critical use cases. | Te | 4 | 25% | 1 | Software Architect | Choose a technology (framework) that will be up to date for a long period and is more appropriate to the project's requirements and content. As quickly as feasible, try to upgrade the old framework to the new framework. Use existing software tools to convert the project if necessary.
5 | 2022-04-08 | Requirement Misunderstood | Some of the software requirements are not fully understood by the team members. The requirement descriptions are uncertian and inadequate. | R | 4 | 50% | 2 | Project Manager | Rearrange the tasks and team to minimize the impact of the absence of the team member. Inform the stakeholders about the situation.
6 | 2022-04-29 | Requirements Changed | One or more requirements of the project are changed after they’ve been implemented. | R | 4 | 50% | 2 | Software Analyst | Inform the stakeholders about the potential delays and the impact of the changed requirement. Derive traceability information to assess requirements change impact; maximize information hiding in the design..
7 | 2022-04-01 | Insufficient Time Available for Team Training | The technical skills required for a development task is underestimated. | P | 3 | 75% | 2.25 | Project Manager | Increase team member participation and information exchange. Team members develop knowledge in various areas and explain it with one another. Experiment with approaches such as extreme programming and pair programming
8 | 2022-05-05 | Low Performance of Database | Database used in the system cannot process the data as fast as expected. | Te | 3 | 50% | 1.5 | Software Architect Config. Manager | Investigate the possibility of buying a higher-performance database.
9 | 2022-05-08 | Software Defect is Discovered | A severe software problem is found soon before the software is delivered | E | 4 | 50% | 2 | Software Tester | Manage effective unit and integration tests to limit the likelihood of hidden flaws in the software. If it is too late, notify the stakeholders of the issue and possible delays.
10 | 2022-03-24 | Reusable Software Components Inconsistencies | Reusable software components contain inconsistencies that means they cannot be reused as planned. | To | 2 | 75% | 1.5 | Development Team | Start to build your own component with the help of the reusable component while solving the inconsistencies.
11 | 2022-04-10 | Demo Failure | A critical use case implementation for the demo failed. | P | 4 | 25% | 1 | Development Team | Inform the stakeholders about the situation, if it is possible ask for an extension, if not, deliver the demo for the parts to arrive in time.
12 | 2022-03-18 | Task Wrongly Understood | A development task assigned to a member of the development team is wrongly understood by the team member. | P | 3 | 50% | 1.5 | Software Analyst, Project Manager | Ensure strong and effective communication between the team members.
13 | 2022-03-15 | Task is Taking Much Time | A development task is taking too much time to complete. | P | 2 | 50% | 1 | Development Team | Use techniques such as pair programming to reduce the time required to complete the task. Reassign work items to other team members f necessary.
14 | 2022-03-15 | Task is Blocked | A development task is blocking another development task to be completed. | P | 4 | 25% | 1 | Project Manager, Development Team | Inform the team member responsible for the task and use programming techniques such as pair programming to reduce the impact of the situation
Note on E2: ====== ID#AAAAIYHr4LA rbalduino (2021-05-01 11:46:41) Type = I (indirect) or D (direct)
Note on F2: ====== ID#AAAAIYHr4K4 mbarnard (2021-05-01 11:46:41) Impact is a numerical value, usually between 1 and 5, that represents the impact to the project if the risk comes true. 5 is a HIGH IMPACT and 1 is LOW IMPACT.
Note on G2: ====== ID#AAAAIYHr4K8 mbarnard (2021-05-01 11:46:41) Probability is the percentage chance that a risk will occur.
Note on H2: ====== ID#AAAAIYHr4LE mbarnard (2021-05-01 11:46:41) Magnitude is the result of the multiplication of Probability and Impact, providing a joint metric suitable for sorting.